## Agile Product Roadmap "Siya Ram
Agile Product Roadmap "Siya Ramen!"
Phase 1: MVP Development (Months 0-1)
Goal: Launch a functional table reservation website with core features.
Sprint 0(Weeks 0-1)Planning & Strategy | Sprint 1 (Weeks 1-2) Project Setup & Basic Pages | Sprint 2 (Weeks 3-4) User Authentication
Define project scope and setup development environment,Create schedules for Minutes of the meeting ,Establish Agile Team and Roles and setup the development and collaboration tools | Set up project structure and hosting. Develop homepage, About Us, and Branches pages. Implement basic navigation (Home, About, Contact).Create wireframes & UI mockups for homepage, navigation, and key pages. | Develop Login and Register functionality. Implement form validation.
Phase 2: Core Features Implementation (Months 1-2)
Goal: Implement key features for reservations and menu.
| Sprint 3 (Weeks 5-6) Reservation System | Sprint 4 (Weeks 7-8) Menu & Contact Us
| Develop reservation feature. Implement confirmation and email notifications. | Create Menu page with categories and pricing. Develop Contact Us form for customer inquiries.
Phase 3: Final Touches & Launch (Month 2-3)
Goal: Improve user experience and prepare for launch.
| Sprint 5 (Weeks 9-10) Pop-up Confirmations | Sprint 6 (Weeks 11-12) Testing & Deployment
| Implement pop-up notifications for successful reservations and contact concerns. | Conduct testing, bug fixes, and deploy the final version.

## Figma UIUX
Back
https://www.figma.com/proto/MJm56HCoG0ysaY5wbsUmWi/IPT?node-id=27-180&p=f&t=txMH6i2PRk67VRf5-1&scaling=scale-down&content-scaling=fixed&page-id=0%3A1&starting-point-node-id=27%3A180

## Project Planning
TEAMS | Development Team | Product & Design Team | Marketing & Outreach Team | Customer Support & Community Management Team | Quality Assurance (QA) Team | Project Manager(Jhon Paul Patatag) | DevOps
Sprint | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
| 0-1weeks | 1-2weeks | 3-4weeks | 5-6weeks | 7-8weeks | 9-10weeks | 11-12weeks
1.Project Setup | Define project scope and setup development environment.
Establish Agile Team and Roles
setup the development and collaboration tools
Communication Management Planning
2.Requirement Gathering | Team Setup & Collaboration Tools | Define core system
| Implement role-based access control. | requirements
`
3.Design and Prototyping
Figma UIUX'!A1
Software Development Phase 1 |  | Architecture & Hosting: Organize files, set up frameworks, configure hosting, and initialize the codebase with Git and dependencies. | Implements login and register functionality, including form validation.
|  | Basic Pages & Navigation: Develop Homepage, About Us, and Branches pages with placeholder content, and implement seamless navigation. | Tests authentication for security and functionality issues.
UI/UX Design: Create wireframes and UI mockups in Figma, designing layouts for key pages (Home, About Us, Branches).
Software Development Phase 2 |  |  |  | Builds reservation feature and confirmation. | Develops Menu page with categories and pricing, and implements Contact Us form.
|  |  |  | Tests reservation system for smooth functionality and bug fixes. | Designs menu layout and Contact Us form
Ensures proper menu display and Contact Us functionality.
Software Development Phase 3 | [5 empty] | Implements pop-up notifications for successful reservations and contact concerns. | Prepares promotional content and online engagement strategies.
[6 empty] | Tests pop-up notifications for proper display and timing. | Gets ready to handle inquiries and customer concerns post-launch.
A

## Dev & Collaboration Tools
Category | Tool/Technology
Developmental Tool | Visual Studio, VS Code
Programming Language | PHP, JavaScript, HTML, CSS
SQL Server | MySQL, phpMyAdmin
Frontend Framework | Bootstrap 5
Collaboration Tools | Figma, Github, Microsoft Teams

## Communication management
Back
Communication Management Planning
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 5
Sprint | 0-1weeks | 1-2weeks | 3-4weeks | 5-6weeks | 7-8weeks | 9-10weeks | 11-12weeks
Team: | DevOps | Development Team | Development Team | Development Team | Development Team | Development Team | Quality Assurance (QA) Team
Meeting: | Project Kickoff Meeting | Project Setup Meeting | Authentication & Form Validation Review | Reservation System Development Review | Menu Page & Contact Us Form Development Review | Pop-up Notification Implementation Review | Pop-up Notification Testing Review
Purpose: | Define project scope and objectives. Set up the development environment. Establish Agile team roles and responsibilities. Select and configure development and collaboration tools. | Discuss project structure, hosting, and basic navigation. | Discuss implementation details, review security measures, and validate login/register functionality. | Discuss implementation of table selection, confirmation, and backend integration. | Discuss progress, ensure proper categorization and pricing for the menu, and implement the Contact Us form correctly. | Ensure that pop-up notifications for successful reservations and contact concerns function correctly and align with user expectations. | Validate that pop-up notifications for successful reservations and contact concerns are displayed correctly and at the right timing.
Location: | Microsoft Teams | Microsoft Teams | Microsoft Teams | Microsoft Teams | Microsoft Teams | Microsoft Teams / Jira / Slack | Microsoft Teams
Frequency: | 2-3 hours | One-time meeting (Week 1, 2 hours) | Scheduled on the last Friday of Sprint 2( 1, 2 hours) | One-time meeting (Week 1, 2 hours) | One-time meeting (Weeks 1,3hours) | One-time meeting (Week 2 hours) | Weekly (3 hour)
Chairperson: | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos
Minutes by: | Jhon Paul Patatag | Alex Carter | Alex Carter | Alex Carter | Alex Carter | Alex Carter | William Anderson
Team: |  | Product & Design Team | Quality Assurance (QA) Team | Quality Assurance (QA) Team | Product & Design Team | Quality Assurance (QA) Team | Marketing & Outreach Team
Meeting: |  | Wireframe & UI Design Review | Security & Functionality Testing Review | Reservation System Testing Review | UI/UX Review of Menu Layout & Contact Us Form | Pop-up Notification Implementation & Testing Review | Promotional Strategy Planning
Purpose: |  | Review and finalize wireframes and UI designs for the homepage, About Us, and Branches pages. | Evaluate authentication security, identify vulnerabilities, and verify proper login/register functionality. | Ensure smooth functionality, identify and resolve bugs in the reservation system. | Finalize wireframes, ensure user-friendly layout for the menu page, and design an accessible Contact Us form. | Ensure that pop-up notifications for successful reservations and contact concerns function correctly, display properly, and appear with correct timing. | Develop and review promotional content and engagement strategies to enhance online presence and customer interaction.
Location: |  | Microsoft Teams | Microsoft Teams | Microsoft Teams | Microsoft Teams / Figma Collaboration | Microsoft Teams | Microsoft Teams / Jira
Frequency: |  | (1 hour) | Weekly (1 hour) | Weekly (1,2 hour) | Weekly(3hours) | Weekly (1,2 hour) | Weekly (1 hour)
Chairperson: |  | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos | Randolf Debalucos
Minutes by: |  | Ethan Walker | William Anderson | William Anderson | Ethan Walker | William Anderson | Ava Mitchell
Team: |  |  |  |  | Quality Assurance (QA) Team |  | Customer Support & Community Management Team
Meeting: |  |  |  |  | Functional Testing Review |  | Post-Launch Customer Support Strategy
Purpose: |  |  |  |  | Validate that the menu page displays correctly and that the Contact Us form works as intended. |  | Prepare for handling customer inquiries, concerns, and feedback efficiently after the website launch.
Location: |  |  |  |  | Microsoft Teams |  | Microsoft Teams / Jira
Frequency: |  |  |  |  | Weekly (2 hour) |  | One-time(1 hour)
Chairperson: |  |  |  |  | Randolf Debalucos |  | Randolf Debalucos
Minutes by: |  |  |  |  | William Anderson |  | Emily Roberts

## Scope of Work
Back | TEAMS | Development Team | Product & Design Team | Marketing & Outreach Team | Customer Support & Community Management Team | Quality Assurance (QA) Team | DevOps
Description
Siya Ramen is a user-friendly online platform designed to streamline table reservations for a seamless dining experience. The website allows customers to make reservations, and receive instant confirmations, enhancing convenience and efficiency.
Project Scope
| Project Setup & Infrastructure | User Authentication | UI/UX Design | Reservation System | Menu & Contact System | Testing & Validation | Customer Engagement & Marketing | Customer Engagement & Marketing
| Set up the project structure, including hosting and file organization. | Develop login and registration functionality with form validation. | Create initial wireframes and UI designs for key pages: | Build a reservation feature and confirmation. | Develop the Menu page with categorized items and pricing. | Test the authentication system for security and functionality. | Prepare promotional content and online engagement strategies. | Prepare promotional content and online engagement strategies.
| Implement basic navigation, including Home, About, and Contact pages. | Ensure secure authentication mechanisms. | Homepage | Implement a pop-up notification for successful reservations. | Implement a Contact Us form for customer inquiries. | Conduct functional testing of the reservation system. |  | Set up a support system for handling customer inquiries post-launch.
|  |  | About Us |  |  | Ensure proper display and functionality of the Menu and Contact Us pages.
|  |  | Branches |  |  | Test pop-up notifications for correct display and timing.
Limitations
| Project Setup & Infrastructure | User Authentication | UI/UX Design | Reservation System | Menu & Contact System | Testing & Validation | Customer Engagement & Marketing | Customer Engagement & Marketing
No mention of email or SMS notifications for user engagement.
| No details on scalability or server capacity—may struggle with high traffic. | Lacks password recovery/reset functionality. | Only includes initial wireframes, but no mention of usability testing. | Does not specify real-time seat availability updates. | No option for online ordering (if applicable). | No mention of load testing to check system stability under heavy traffic. | No integration with social media marketing strategies.
| Hosting provider and security measures are not specified. | No mention of social login options (e.g., Google, Facebook). | No mention of responsive design for mobile/tablet users. | No handling of cancellations or modifications to reservations. | Lacks customer reviews or ratings for menu items. | Absence of security penetration testing to detect vulnerabilities. | Lacks loyalty programs or customer retention strategies.
| No mention of database setup, which is crucial for reservations. | Absence of multi-factor authentication (MFA) for added security. | Lacks accessibility considerations (e.g., screen readers, color contrast). | Absence of a waitlist or overbooking prevention system. | No mention of real-time updates for menu availability. | No details on cross-browser compatibility testing.

## User stories and Requirements
Back
Features | Functional Requirements | Non-Functional Requirements | Constraints
User Management & Authentication | User Authentication | Performance | Technical Constraints
User Registration – Users can create an account with email verification. | Users can register and log in securely. | System should load pages within 3 seconds on average. | The project must use PHP & MySQL for backend development.
User Login & Logout – Secure login with password encryption. | System validates input fields (e.g., email format, password strength). | Must handle at least 100 concurrent users without performance degradation. | The system should not rely on external paid APIs for core functionality.
Password Recovery – Users can reset their password via email. | Password encryption and secure authentication. |  | Hosting must support LAMP stack (Linux, Apache, MySQL, PHP).
Role-based Access Control – Users and admins have different access levels. |  |  | Time Constraints
Reservation System | Reservation System | Security | MVP development must be completed in 3 months (12 weeks).
Table reservation– Users can reserve tables and reservation time. | Users can make a reservation. | Encrypted password storage using bcrypt or equivalent. | Each sprint must deliver working features on a bi-weekly basis.
Real-Time Availability – Prevents double booking by displaying table availability. | System sends confirmation via email and on-screen pop-up notifications. | Secure HTTPS connection for data transmission. | Budget Constraints
Reservation Confirmation – Users receive confirmation via pop-up and email. | Admin can manage reservations (approve, cancel, modify). | Role-based access control for user and admin privileges. | Must use free or open-source tools for development (e.g., GitHub, MySQL, Bootstrap).
Reservation Management – Users can view, modify, or cancel reservations. | Users can view their reservation history. |  | Hosting and domain costs should not exceed a predefined budget.
Admin Reservation Control – Admins can approve, reject, or reschedule bookings. |  |  | Team Constraints
Menu & Ordering | Menu & Contact Us | Usability & Accessibility | The team follows Agile methodology with defined roles.
Dynamic Menu Display – Categorized menu with prices and descriptions. | Users can browse a categorized menu with pricing. | UI should be intuitive for users of all experience levels. | Limited team size with dedicated front-end and back-end developers.
Search & Filter – Users can search menu items or filter by category. | Users can submit inquiries through a contact form. | Website should be mobile-friendly and fully responsive.
Special Offers & Discounts – Display promotions and discounts on the menu. | System sends confirmation for submitted inquiries. | Compliant with WCAG 2.1 (Web Content Accessibility Guidelines).
Contact & Customer Support | Navigation & UI | Scalability & Maintainability
Contact Us Form – Users can submit inquiries, complaints, or feedback. | Homepage, About Us, and Branches pages are accessible. | System should support future feature expansions.
Inquiry Notifications – Users get a confirmation after submitting an inquiry. | Seamless navigation between pages (Home, About, Contact). | Codebase should follow MVC architecture for better maintainability.
Admin Inbox – Admins receive and manage customer messages. | Responsive UI for different devices.
UI/UX & Navigation | Notifications & Alerts | Reliability & Availability
Homepage Design – Displays brand story, featured dishes, and promotions. | Pop-up notifications for reservation confirmation and contact inquiries. | System uptime should be 99.9% to ensure availability.
About Us Page – Showcases restaurant background and mission. | Email notifications for successful reservations. | System should auto-recover from minor failures.
Branches Page – Lists restaurant locations with Google Maps integration.
Navigation Menu – Smooth transition between pages for better user experience.
Mobile Responsiveness – Ensures a smooth experience on all devices.
Notifications & Alerts | Testing & Deployment
Pop-Up Notifications – Alerts for successful reservations and inquiries. | System undergoes functionality testing before deployment.
Email Notifications – Automated confirmation emails for users. | Final version is deployed on a live hosting environment.
Admin Alerts – Admins get notified of new reservations or inquiries.
Testing & Deployment
Bug Tracking & Fixing – Continuous testing to ensure smooth functionality.
Final Deployment – Hosting the website on a live server.

## DevOps
Back
DevOps
| Name | Role | Responsibility
| Randolf Debalucos | Devops | ensures smooth development, deployment, and maintenance of the Siya Ramen reservation system. Their responsibilities align with the Agile roadmap and sprint cycles.

## development team
Back
Development Team
| Name | Role | Responsibility
| Alex Carter | Team Lead | Oversees the entire development process and ensures the team follows best practices.
| Sophia Reyes | Frontend Team (Frontend Developer) | Develops the user interface and ensures a smooth user experience.
| David Kim | Frontend Team (UI/UX Designer) | Designs the visual layout and user experience of the platform.
| Ryan Thompson | Backend (Backend Developer) | Manages server-side logic, database interactions, and API development.
| Linda Wu | Backend (Database Administrator) | Oversees database structure and performance.
| Kevin Patel | Testing & Security (QA Engineer) | Tests the platform for bugs, usability, and security vulnerabilities.
| Maria Gonzalez | Testing & Security (Cybersecurity Specialist) | Protects the platform from security threats.

## Product & Design Team
Back
Product & Design Team
| Name | Role | Responsibility
| Ethan Walker | Team Lead | Oversees the product roadmap, feature prioritization, and overall platform strategy.
| Noah Sanders | Graphic Designer | Handles branding, visuals, and promotional design assets.
| Emma Castillo | Research & Strategy Team(User Researcher) | Conducts research to improve user experience and product decisions.
| Liam Hayes | Research & Strategy Team(Content Strategist) | Develops content for the website, ensuring clarity and engagement.

## Marketing & Outreach Team
Back
Marketing Team
| Name | Role | Responsibility
| Ava Mitchell | Team Lead | Leads marketing strategies, brand positioning, and outreach campaigns.
| James Carter | Digital Marketing (SEO & Content Marketing Specialist) | Optimizes the website for search engines and manages content marketing.
| Sophia Rivera | Digital Marketing (Social Media Manager) | Manages social media platforms and community engagement.
| Liam Foster | Digital Marketing (Paid Ads & Email Marketing Specialist) | Runs paid advertising campaigns and email marketing.
| Mia Johnson | Outreach & Partnerships Team(Public Relations & Media Specialist) | Manages media relations and public outreach efforts.
| Ethan Williams | Outreach & Partnerships Team(Partnership & NGO Liaison) | Builds relationships with NGOs, government agencies, and corporate sponsors.

## Customer Support & Community Ma
Back
Customer Support Team
| Name | Role | Responsibility
| Emily Roberts | Team Lead | Oversees customer support operations and manages user engagement.
| Daniel Parker | Customer Support Team(Support Specialist - Donations & Payments) | Handles inquiries related to donations, investments, and payment processing.
| Samantha Lee | Customer Support Team(Support Specialist - Farmers & Marketplace) | Assists farmers and buyers with marketplace-related issues.
| Chris Anderson | Customer Support Team(Technical Support Specialist) | Assists users with technical issues related to the website.
| Olivia Scott | Community Engagement Team(Community Engagement Coordinator) | Builds an active community among donors, farmers, and stakeholders.
| Jacob Hernandez | Community Engagement Team(Volunteer & Outreach Coordinator) | Engages volunteers and NGOs to support the platform’s initiatives.

## Quality Assurance (QA) Team
Back
Quality Assurance (QA) Team
| Name | Role | Responsibility
| William Anderson | Team Lead | Oversees content creation, knowledge sharing, and educational materials for the platform.
| Isabella Carter | Content Creation Team(Content Writer & Editor) | Writes, edits, and manages website content, blogs, and educational materials.
| Noah Bennett | Content Creation Team(Multimedia Specialist) | Designs and produces visual and video content for educational and marketing purposes.
| Ava Thompson | Content Creation Team (Social Impact Storyteller) | Collects and shares real-life stories of impact from farmers, donors, and beneficiaries.
| James Collins | Knowledge & Research Team(Agricultural Expert & Knowledge Lead) | Provides expertise on agricultural best practices and guidelines for farmers.
| Sophia Ramirez | Knowledge & Research Team(Data & Research Analyst) | Collects and analyzes data on farming, donations, and marketplace trends.
| Ethan Walker | Knowledge & Research Team(Weather & Climate Specialist) | Provides weather updates and climate adaptation strategies for farmers.